## Tabelle1
Budget plan | WG6 |  |  |  |  | Date | 2013-11-27
Project | Suspension Testing - EU wide solution |  |  |  | Beaujean | Version | 2.0
Cost distribution plan
Step | Headline | Content | Chairman | Contributing companies | Secretary General [labour days] | Policy manager [labour days] | Tech. Advisor [labour days] | Travel&Accom. [€]* | External Services [€]
1 | Meeting with Mr. Nissler | Mutual agreement on targets and expected results | x |  | 1.5 |  | 1.5 |  |  | 1.5 | 1.5
2 | WG6 - Working Session #1 | Discussion on the tender content, Creation of tender spec draft version Identification of possible tender candidates | x | x |  | 1.5 | 1.5 |  |  | 1.5 | 1.5
3 | WG6 - Working Session #2 | Finallization of the tender specs Finalization of the tender rules / dates | x | x |  | 1.5 | 1.5 |  |  | 1.5 | 1.5
4 | Distribution of the Tender Documents | Posting the tender Sending out the tender specs to the candidates |  |  | 0.5 |  |  |  |  | 0.5
5 | Collection of the Tender Offers | Receiving the tender documents Checking for formal completeness |  |  | 0.5 |  |  |  |  | 0.5
6 | WG6 - Working Session #3 | Technical assessment of all candidates. Short list 2 candidates | x | x |  | 1.5 | 1.5 |  |  | 1.5 | 1.5
7 | WG6 - Working Session #4 | Face-to-face meetings with the short list candidates. Desicion on tender winner. | x | x |  | 1.5 | 1.5 |  |  | 1.5 | 1.5
8 | Meeting at the tender candidate | Visit at the tender winner. Mutal agreement on project plan. | x |  |  |  | 1 | 500 |  |  | 1
9 | Vehicles & Suspension | Costs for renting vehicles Preparation of suspension and shock absorbers |  | x |  |  |  |  | 5000
10 | Validation | Practical Tests Completion of the test results Draft version of homolagion regulations Comprehensive Final report |  | x |  |  |  |  | 36000
11 | Reception of the tender results | Openening of the tender results. Check on formal completeness and quality If it does not meet the formal expectation it needs to be adressed back to tenderer. (Eventually a face-to-face-meeting is needed) | x |  | 0.5 |  | 1 |  |  | 0.5 | 1
11 | Distribution of the Tender results | Sending out the results to all stakeholders |  |  | 0.5 |  |  |  |  | 0.5
12 | WG6 - Working Session #5 | Finalization of the homologation regulation proposal | x | x |  | 1.5 | 1.5 |  |  | 1.5 | 1.5
13 | Meeting with Mr. Nissler | Hand over of proposal to Mr. Nissler | x |  | 1.5 |  | 1.5 |  |  | 1.5 | 1.5
|  |  | 9 | 7 | 5 | 7.5 | 12.5 | 500 | 41000
|  | Costs per day | 0 | 0 | 500 | 350 | 500
|  | VAT (secretary) | [6 empty] | 1100
| Project overall costs | [7 empty] | 53975
Approvals | [7 empty] | * Travels and Accommodation to/in Brussels not included
Date
Signature
| WG Chairman | EGEA office | Technical Advisor
Approval
Date
Signature
EGEA Board